## Sheet1
Description of Risk | How will it affect the team | Frequency | Danger | Overall Score | Risk Factor | Ways to Reduce Risk | What to do in event of risk occurring
Computers not working / unable to access computers or suitable hardware/software | Team unable to work together on computer-based tasks until another suitable computer or room is found | 1 | 1 | 1 | Low | Make use of portable computers such as laptops where possible. Check ahead of time the situation with computers at the chosen meeting point. Have alternate meeting locations planned ahead of time. | Re-arrange meeting location and possibly time, and contact all other team members the new information. If too close to time of meeting wait for all members (not including those that are running late) and move to secondary meeting location - or find another suitable location. Work in a coffee shop using laptops and mobile devices if another lab / computer room cannot be found.
Late to meetings | Delays to the start of meetings, reducing the amount of time available for the team to work together | 2 | 1 | 2 | Low | Ensure consistent, regular communication between team members using agreed methods. Members to inform team if they are running late, and a register taken of all members recording attendance and times late to meetings. Project Lead to send reminders and updates as to time / location of meetings, and to make agendas freely available using agreed methods. Regular meetings to be held at same time and place to increase consistency. Project Lead to personally contact members who are at greater risk of running late with reminders of expectations and time/location of meeting | Depending on team members absent, meeting may begin without them. Team to contact missing member(s) and to move on to alternative agenda items.
Meeting place unavailable for team meeting | Team unable to meet at arranged place and time, delay to start of meeting while location is re-arranged and suitable room found. Potential postponement to meeting. | 1 | 2 | 2 | Low | Make use of portable computers such as laptops where possible. Check ahead of time the situation with computers at the chosen meeting point. Have alternate meeting locations planned ahead of time. | Re-arrange meeting location and possibly time, and contact all other team members the new information. If too close to time of meeting wait for all members (not including those that are running late) and move to secondary meeting location - or find another suitable location. Work in a coffee shop using laptops and mobile devices if another lab / computer room cannot be found.
No coffee/snacks at meetings | Total disregard for the happiness and wellbeing of team members will result in reduced productivity and lack of attendance at meetings | 1 | 1 | 1 | Low | Create rota to share responsibility for who will bring what to meetings. Ensure team knows well in advance the expectations - who will bring what and when - to ensure they have sufficient time to acquire the items. | Quick run to the nearest coffee shop / vending machine to acquire suitable drinks and snacks where appropriate. Do without snacks and have an unhappier experience.
Peter's additional needs | Wheelchair limits access to particular buildings and rooms. Particular buildings are inaccessible to PS beyond the ground floor. Anxiety and general health issues may result in PS being present for a meeting or working session, but unable to contribute Due to support worker absence, a temporary support worker may be present who is unfamiliar with team and work, reducing the speed and effectiveness of PS' contributions to meetings and work sessions | 3 | 1 | 3 | Medium | Limit PS' anxiety through consistent and regular communication, ensuring he knows what he has to do, by when, and how it ties in to the group project as a whole Ensure all meetings take into account the restrictied access for the wheelchair - use of the Zone in Ellison building is on the ground floor, is spacious and has tables and computers where groups can work effectively together. PS can work from home using his own laptop, and by brining it in to meetings and sessions he will have access to up to date files and works to compile and collate. General health issues - see Short Term and Long Term Sickness above | PS to inform team and tutors at earliest convenience, offering as much information as is possible. Communicate with team, tutors and student support to minimise duration of restricted access. Communicate with team to ensure that, where possible, work can continue without PS involvement. Temporary project leadership may be required from another member of the team to ensure all task documentation is completed.
Sickness, long-term and unexpected | Unable to complete individual work would affect only the individual concerned. Group work would increse the demands and expectations of the other team members, possibly resulting in a weakened final project | 1 | 3 | 3 | Medium | Ensure consistent, regular communication between team members using agreed methods both formal and informally, so that team members are aware of any change in personal situations. Team members to inform team of any upcoming appointments that might clash with meetings or interfere with deadlines and progression of work. All completed work to be stored in a centralised area, as agreed by team. Incomplete work and work in progress should also be made available to the team in a suitable format so that it is available to all should they need it. | Team to consider options, project lead to communicate with absent member and tutors to inform them of the situation at the earliest opportunity. Critical tasks reassigned, potential removal of team member from team and reduction in number of tasks team are responsible for.
Sickness, short-term and unexpected | Individual team members left out of group decisions, potentially unable to reach a consensus if more than one member absent at the same time. Unable to present work or show progress, and lack of communication to resolve projects. General reduced level of confidence in the finished project and increased anxiety of othe rmembers. | 1 | 2 | 2 | Low | Ensure consistent, regular communication between team members using agreed methods both formal and informally, so that team members are aware of any change in personal situations. Team members to inform team of any upcoming appointments that might clash with meetings or interfere with deadlines and progression of work. All completed work to be stored in a centralised area, as agreed by team. Incomplete work and work in progress should also be made available to the team in a suitable format so that it is available to all should they need it. | Team to consider how long individual member will be absent. Project lead to review the critical path to see if the member was doing a critical task, and if not then no further action; if so then other team member(s) to be given some of the absent member's critical work to ensure that work can proceed relatively unaffected.
Team member not meeting deadlines | Will result in uncertainty when major deadlines would be hit for rest of team, potentially resulting in a weakened final project due to poor cohesion and cohesiveness | 1 | 2 | 2 | Low | Ensure consistent, regular communication between team members using agreed methods both formal and informally, so that team members are aware of any change in personal situations. Individual team members to keep team updated as to their progress on individual tasks. Project Lead to keep up to date with individual progression, so that an overall picture of the progress of the project is maintained at all times. Project Lead to assign sufficient time to individual tasks and to ensure that deadlines are realistic and manageable, and that set deadlines are met by team members. | Project lead to hold 1:1 meeting with member concerned to discuss matters. Communicate and discuss situation with tutors.
Unable to access GitHub or GoogleDrive | Team will be unable to upload, download or share work between them | 1 | 3 | 3 | Medium | Ensure that local copies of all files are made on safe and reliable media. Team members to ensure that any non-centralised resource is available at the correct meetings. | Team members to communicate with Project Lead and each other, to ensure all are aware of the problem. Project Lead to advise members what resources will be required at any upcoming meeting, and to organise resources and communications appropriately. Alternative, temporary centralised network drive to be used to store files (GoogleDrive in the event of a GitHub failure)
Unexplained absence from meetings | Individual team members left out of group decisions, potentially unable to reach a consensus if more than one member absent at the same time. Unable to present work or show progress, and lack of communication to resolve projects. General reduced level of confidence in the finished project and increased anxiety of othe rmembers. | 1 | 2 | 2 | Low | Ensure consistent, regular communication between team members using agreed methods. Members to inform team if they are running late, and a register taken of all members recording attendance and times late to meetings. Project Lead to send reminders and updates as to time / location of meetings, and to make agendas freely available using agreed methods. Regular meetings to be held at same time and place to increase consistency. Project Lead to personally contact members who are at greater risk of absenteeism with reminders of expectations and time/location of meeting | Depending on team members absent, meeting may begin without them. Team to contact missing member(s) and to move on to alternative agenda items. Consensus on group tasks to be reached without input of absent member, tasks and deadlines reassigned where possible. Individual team members are responsible for their own part of the project and it will not affect 80% of the marks of other team members.
|  |  |  | 0 | Low
|  |  |  | 0 | Low
|  |  |  | 0 | Low
|  |  |  | 0 | Low
|  |  |  | 0 | Low
|  |  |  | 0 | Low
|  |  |  | 0 | Low