## Communications
Date | Members | Conversation | Follow up, if any
24/01/18 | All | Team meeting #1 - see Meeting 1 for minutes
29/01/18 | PS MB | Online conversation re: MoSCoW analysis and analysis tasks. Task not initially assigned in Meeting 1. | MB to do MoSCow document
29/01/18 | All | Online conversation re: Task distribution, task completion, class diagrams, ideas of the implementation of task classes and UI design | PS to review classes
30/01/18 | All | Online conversation querying aspects of the system analysis and design
30/01/18 | All | PS reminds group about meeting time the following day
31/01/18 | All | Team meeting #2 - see Meeting 2 for minutes
31/01/18 | All | PS sent meeting notes and draft agenda for meeting #3 to all members | PS to double check agenda needed for next meeting
2018-01-02 | All | Sent finalised minutes from meeting #2 and template for the skills audit to all members | Members to complete skills audit
2018-01-02 | All | SC set up a GitHub repository for the team members to use, and invited all members to join | All members to accept invitation. PS to transfer all required files to GitHub to back-up and make available there.
2018-04-02 | All | MB uploaded Statement of Purpose document to GoogleDrive | PS to give review and comment, but other members are free to comment
2018-05-02 | PS | Gave feedback to MB on Statement of Purpose document
2018-05-02 | PS SC | Update requested as to current progress and situation with the ERD and database
2018-05-02 | All | Class diagram discussed about how to implement a state
2018-06-02 | All | Informed group as to time, date and location of meeting with CB. | PS to speak to CB regarding meeting on ground floor
2018-07-02 | All | MB and SC used messenger to inform that they would be late to the meeting
2018-07-02 | All | PS updated group as to completion of Project Proposal and other documents, asking group to proof-read and ask questions. | Proof read Project Proposaland agreeing that they are complete, or adding fresh requirements
2018-08-02 | All | SC asked for help with using the project discussion board
2019-08-02 | All | MW enquired about tables for the database which would store recurring tasks
2019-08-02 | All | PS informed group that SC had updated the project timeline and he was making a backup on GitHub
2018-08-02 | All | MW enquired about the handing in of the Skills Audit, and the deadline
2018-09-02 | All | PS informed group that Project timeline was again up to date and upload to GitHub
2018-12-02 | SC PS | Discussion on progress of the ERD and SC uploaded 3 copies of the ERD. | Need to clarify which version of the uploaded ERD files is the most recent
13/02/2018 | MB | Apologies sent to group; MB unable to attend group meeting.
14/02/2018 | All | PS messaged group to inform them he was ill and wouldn't be able to attend the meeting with Cliff.
16/02/2018 | All | Minutes of meeting 4 completed and posted online - PS updated group
16/02/2018 | All | Acknowledgement that a basic DB was setup and linked
19/02/2018 | All | Confirmation that the database and some GUIs had been looked at and tested. Confirmation that members should be writing GUI code as a prototype to test if current designs fitted the system.
20/02/2018 | All | Communication confirming that the meeting to be held on Wed 21st Feb would be cancelled due to bad weather
20/02/2018 | All | PS asked all team members to inform him of their current level of progress and what task they were currently working on.,
2018-09-02 | All | PS informed group that meeting may not be possible | PS to update group later in week
2018-11-03 | MB PS | MB informed PS of meta data issue
2018-12-03 | All | MW sent screenshots of GUIs to the group
15/03 | All | Discussion on meeting with Cliff that the group all missed
15/03 | All | MW sent screenshots of GUIs to the group
15/03 | All | Discussion of database connection
17/03 | All | MW asked a question about GitHub | MB replied with a GitHub programme
20/03 | All | Meeting cancelled for that week
20/03 onwards | All | Small discussions about different parts of the programme. For example, how we handled repeating tasks. Also, some discussion on the login system. Most discussions about the system were done by the comments in GitHub. | Some issues arose during our group chats outside of university hours. These issues were minor and were of no real cause for drastic action or concern, any bigger issues that were encountered were logged within the problems log included in this document. Generally these issues were 'talked out' during the chats and a resolution was met within the chat session or when we met personally the following day (refer to screenshot attached).
Formulas:
Date = [Date, row above]

## Problems
Date | Risk Factor | Problems Identified | Suggested solution | Date Resolved | Alternative to Original Resolution
29/01/18 | Low at present changing to high if not resolved | Lack of MoSCow | MB tasked with completing MoSCoW analysis before meeting on 31/01/18 | 30/01/2018
31/01/18 | Very low at present, changing to moderate to high once programming begins | Class diagram - how are tasks to show whether they are pending / allocated / completed | Use an abstract class to monitor / store state of task |  | A string variable was declared in task class to store the state of a task (15/4/18).
31/01/18 | Moderate to high | Database software not agreed | Access database has been suggested, with a Java interface. Decision is still pending by SC | 13/02/2018
31/01/18 | Low at present, changing to Very High as the system progresses | Algorithm to determine allocation of task to caretakers not fully agreed upon. Tasks to be given a flexible priority system to determine how urgently they need to be completed. Incomplete tasks would increase in priority the longer they remain incomplete. Caretakers to be automatically assigned tasks, no way to chose their own tasks. Tasks that are incomplete may be reassigned to other caretakers. Caretakers can "save" or "store", flagging a task as incomplete but ensuring that they keep it. Caretaker preferences have to be taken into consideration - tasks they are good at and like should be given to the same caretaker, tasks that are disliked by all should be allocated on a rotating basis - all of this needs to be done FAIRLY | Agreement needs to be made as to the requirements for the algorithm at an early stage to allow for incorporation into other tasks of the project if required. MW determined the algorithm by trying out different solutions. The current algorithm works by tracking which caretaker has the highest preference rating for a category. | 15/04/18
31/01/18 | Very low at present, changing to moderate to high once programming begins | Statement of Purpose missing from documentation | Task assigned to MB to complete before next meeting (07/02/18) | 2018-05-02
2018-07-02 | Low at present | Does the Class Diagram require a separate class for Database | A separate class was used to handle the communication with the database. This meant that it was easy to connect to the database and re-use SQL query. | 2018-08-03
2018-11-03 | moderate | Issues with db and meta data | A solution was found online wereby everytime we opened the database we needed to clear the meta data. | 2018-11-03
2018-12-03 | Low | Peter had to change support worker. This may lead to a slower amount of work being completed, for a short period of time. | N/A | 2018-12-03
2015-08-04 | moderate | Max merged the git hub branches, but it went wrong and he lost 3 days of code | Max to try to get work back or redo it | 15/04/18
30/04/18 | Low/Moderate | Max and Sam worked on the same arae of the project (User Interface for a manager) without firstly consulting each other about doing so. | Max's work was sacrificed in favour of both team members coming together to work on Sam's version of the UI. | 30/04/18