## GANTT
|  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
|  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Task | Task # | Member | Comments | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-27 | 2018-01-28 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-06-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13
Deadlines |  |  |  | Week 2 Wed: MET; Week 3 Wed: MET
Code of Conduct 1.1 | 1.1 |  |  | Week 2 Wed: 2 | 2
Quality Document 1.2 | 1.2 |  |  | Week 3 Wed: 2 | 2
Plan for Task 7 7.1 | 7.1 |  |  | Week 2 Wed: 2; Week 2 Thu: 2; Week 2 Fri: 2; Week 2 Sat: 2; Week 2 Sun: 2 | 10
Plan for Task 8 8.1 | 8.1 |  |  | Week 2 Wed: 2; Week 2 Thu: 2; Week 2 Fri: 2; Week 2 Sat: 2; Week 2 Sun: 2 | 10
MoSCoW Analysis 2.4 | 2.4 |  |  | Week 3 Mon: 2; Week 3 Tue: 2; Week 3 Wed: 2 | 6
Statement of the purpose of the system 2.1 | 2.1 |  |  | Week 3 Mon: 2; Week 3 Tue: 2; Week 3 Wed: 2 | 6
Documentation of the data model - ERD draft 6.1 | 6.1 | [121 empty] | 5 | bar: Week 3 Wed to Week 3 Sun
Database tables 6.3 | 6.3 | [121 empty] | 8 | bar: Week 3 Wed to Week 4 Wed
UI Design (Flow Chart) 11.1 | 1.1 | [121 empty] | 3 | bar: Week 4 Mon to Week 4 Wed
Process for testing and reporting on testing 4.2 | 4.2 | [121 empty] | 8 | bar: Week 3 Wed to Week 4 Wed
Class Diagram 2 - Revised Plans 3.4 | 3.4 | [121 empty] | 8 | bar: Week 3 Wed to Week 4 Wed
UML Use Case Diagram 2.3 | 2.3 | [121 empty] | 8 | bar: Week 3 Wed to Week 4 Wed
Risk Analysis 1.6 | 1.6 |  |  | Week 4 Thu: 2 | 2
Logs of Progress, problems and solutions 1.8 | 1.8 | [121 empty] | 8 | bar: Week 2 Fri; Week 3 Fri; Week 4 Fri; Week 5 Fri; Week 6 Fri; Week 7 Fri; Week 8 Fri; Week 9 Fri
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on I4: Email Dan about group Done -Peter Smith
Note on W4: Project Proposal and Skills Audit by midnight -Peter Smith
Note on DM4: Software and all other documentation at presentation in -Peter Smith

## TaskSummary
Task | Member | Comments | Not Started | In Progress | Completed
Task 1 - Project Management | PS
Code of Conduct | PS
Quality Document | PS
Skills Audit | PS
Project Proposal | PS
Risk Analysis | PS
GANTT Chart | PS | ONGOING One day a week after a meeting to update
Logs of Progress, problems and solutions | PS
Records of Communication | PS | NO DATE -- ONGOING
Task 2 - Requirements Analysis | MB
Statement of the purpose of the system | MB
UML Use Case Diagram | MB
Set of Use Case descriptions | MB
MoSCoW Analysis | MB
Task 3 - Software Analysis | PS
Class diagram | PS
State machine diagrams | PS
Sequence diagrams and/or activity diagrams | PS
Task 4 - Testing | GROUP
Process for testing and reporting on testing | GROUP
A full record of all testing | GROUP
Task 5 - Task Entry Component | SC
Functionality to allow appropriate user to add new regular one-off tasks | SC
Functionality to allow appropriate user to add relevant information about tasks | SC
Safeguards against common errors | SC
Functionality to present a sortable list of existing tasks | SC
Functionality to allow the user to select and edit task information | SC
Task 6 - Data Component | SC
Documentation of the data model (Entity relationship diagram, etc) | SC
Method for persistent storage of data | SC
Appropriate methods that allow other components to query and update the data | SC
Write database class list | SC
Task 7 - Task Allocation Component | MW
Functionality to allow to assign tasks to staff | MW
Functionality to provide a clear statement of daily tasks to staff | MW
Functionality to provide a sortable list of tasks, indicating tasks that have not be assigned | MW
Safeguards to prevent common errors | MW
Task 8 - User Account Component | MB
Functionality to provide a way for users to log on | MB
Functionality for adding new users | MB
Functionality for removing users | MB
Functionality for editing user information | MB
Functionality for categorisation of users with appropriate access features | MB
Software interfaces that provide information to other components when they need to know the identity of the current user | MB
Functionality to allow users to update security information (passwords) | MB
Task 9 - Task Logging | MW
Functionality to allow staff to log the completion of regular and one-off tasks | MW
Functionality to allow staff to easily find tasks assigned to them, either completed or pending | MW
Functionality to allow staff (including managers) to edit the record of tasks completed | MW
Task 10 - Reporting Component | GROUP
Functionality to provide reports on the current status of tasks, particularly overdue tasks | GROUP
Functionality to provide reports on the historic performance of staff, particularly signs of poor performance or unequal work load | GROUP
Functionality to provide reports on the historic completion of tasks, particularly tasks that are often overdue or not completed satisfactorily. | GROUP

## TaskList
Task | Task | Member | Comments | Task # | Task Name | Concatenate
0.1 | UI Design (Flow Chart) | GROUP |  | 1 | Project Management | UI Design (Flow Chart) 0.2
0.2 | UI Finished | GROUP |  | 2 | Requirements Analysis | UI Finished 1.2
1.2 | Quality Document | PS |  | 3 | Software Analysis | Quality Document 1.3
1.3 | Skills Audit | PS |  | 4 | Testing | Skills Audit 1.4
1.4 | Project Proposal | PS |  | 5 | Task Entry Component | Project Proposal 1.5
1.5 | Risk Analysis | PS |  | 6 | Data Component | Risk Analysis 1.6
1.6 | GANTT Chart | PS | ONGOING One day a week after a meeting to update | 7 | Task Allocation Component | GANTT Chart 1.7
1.7 | Logs of Progress, problems and solutions | PS |  | 8 | User Account Component | Logs of Progress, problems and solutions 1.8
1.8 | Records of Communication | PS | NO DATE -- ONGOING | 9 | Task Logging | Records of Communication 2.1
2.1 | Statement of the purpose of the system | MB |  | 10 | Reporting Component | Statement of the purpose of the system 2.2
2.2 | UML Use Case Diagram | MB |  |  |  | UML Use Case Diagram 2.3
2.3 | Set of Use Case descriptions | MB |  |  |  | Set of Use Case descriptions 2.4
2.4 | MoSCoW Analysis | MB |  |  |  | MoSCoW Analysis 3.1
3.1 | Class Diagram | PS |  |  |  | Class Diagram 3.2
3.2 | Class Diagram 1 - Initial Plans | PS |  |  |  | Class Diagram 1 - Initial Plans 3.3
3.3 | Class Diagram 2 - Revised Plans | PS |  |  |  | Class Diagram 2 - Revised Plans 3.4
3.4 | Class Diagram 3 - Finalised Plans | PS |  |  |  | Class Diagram 3 - Finalised Plans 3.5
3.5 | State machine diagrams | PS |  |  |  | State machine diagrams 3.6
3.6 | Sequence diagrams and/or activity diagrams | PS |  |  |  | Sequence diagrams and/or activity diagrams 4.1
4.1 | Process for testing and reporting on testing | GROUP |  |  |  | Process for testing and reporting on testing 4.2
4.2 | A full record of all testing | GROUP |  |  |  | A full record of all testing 5.1
5.1 | Functionality to allow appropriate user to add new regular one-off tasks | SC |  |  |  | Functionality to allow appropriate user to add new regular one-off tasks 5.2
5.2 | Functionality to allow appropriate user to add relevant information about tasks | SC |  |  |  | Functionality to allow appropriate user to add relevant information about tasks 5.3
5.3 | Safeguards against common errors | SC |  |  |  | Safeguards against common errors 5.4
5.4 | Functionality to present a sortable list of existing tasks | SC |  |  |  | Functionality to present a sortable list of existing tasks 5.5
5.5 | Functionality to allow the user to select and edit task information | SC |  |  |  | Functionality to allow the user to select and edit task information 6.1
6.1 | Documentation of the data model - ERD draft | SC |  |  |  | Documentation of the data model - ERD draft 6.2
6.2 | Documentation of the data model - ERD complete | SC |  |  |  | Documentation of the data model - ERD complete 6.3
6.3 | Database tables | SC |  |  |  | Database tables 6.4
6.4 | Method for persistent storage of data | SC |  |  |  | Method for persistent storage of data 6.5
6.5 | Appropriate methods that allow other components to query and update the data | SC |  |  |  | Appropriate methods that allow other components to query and update the data 6.6
6.6 | Write database class list | SC |  |  |  | Write database class list 7.1
7.1 | Plan for Task 7 | MW |  |  |  | Plan for Task 7 7.2
7.2 | Functionality to allow to assign tasks to staff | MW |  |  |  | Functionality to allow to assign tasks to staff 7.3
7.3 | Functionality to provide a clear statement of daily tasks to staff | MW |  |  |  | Functionality to provide a clear statement of daily tasks to staff 7.4
7.4 | Functionality to provide a sortable list of tasks, indicating tasks that have not be assigned | MW |  |  |  | Functionality to provide a sortable list of tasks, indicating tasks that have not be assigned 7.5
7.5 | Safeguards to prevent common errors | MW |  |  |  | Safeguards to prevent common errors 8.1
8.1 | Plan for Task 8 | MB |  |  |  | Plan for Task 8 8.2
8.2 | Functionality to provide a way for users to log on | MB |  |  |  | Functionality to provide a way for users to log on 8.3
8.3 | Functionality for adding new users | MB |  |  |  | Functionality for adding new users 8.4
8.4 | Functionality for removing users | MB |  |  |  | Functionality for removing users 8.5
8.5 | Functionality for editing user information | MB |  |  |  | Functionality for editing user information 8.6
8.6 | Functionality for categorisation of users with appropriate access features | MB |  |  |  | Functionality for categorisation of users with appropriate access features 8.7
8.7 | Software interfaces that provide information to other components when they need to know the identity of the current user | MB |  |  |  | Software interfaces that provide information to other components when they need to know the identity of the current user 8.8
8.8 | Functionality to allow users to update security information (passwords) | MB |  |  |  | Functionality to allow users to update security information (passwords) 9.1
9.1 | Functionality to allow staff to log the completion of regular and one-off tasks | MW |  |  |  | Functionality to allow staff to log the completion of regular and one-off tasks 9.2
9.2 | Functionality to allow staff to easily find tasks assigned to them, either completed or pending | MW |  |  |  | Functionality to allow staff to easily find tasks assigned to them, either completed or pending 9.3
9.3 | Functionality to allow staff (including managers) to edit the record of tasks completed | MW |  |  |  | Functionality to allow staff (including managers) to edit the record of tasks completed 10.1
10.1 | Functionality to provide reports on the current status of tasks, particularly overdue tasks | GROUP |  |  |  | Functionality to provide reports on the current status of tasks, particularly overdue tasks 10.2
10.2 | Functionality to provide reports on the historic performance of staff, particularly signs of poor performance or unequal work load | GROUP |  |  |  | Functionality to provide reports on the historic performance of staff, particularly signs of poor performance or unequal work load 10.3
10.3 | Functionality to provide reports on the historic completion of tasks, particularly tasks that are often overdue or not completed satisfactorily. | GROUP |  |  |  | Functionality to provide reports on the historic completion of tasks, particularly tasks that are often overdue or not completed satisfactorily.

## Attendance
Team Member | 2018-01-24 | 2018-01-31 | 2018-02-07 | 2018-02-14 | 2018-02-21
Peter Smith | Y | Y
Sam Connelly | Y | Y
Michael Buglass | Y | Y
Max Walsh | L | L
Note on B5: About 20mins late -Peter Smith